## Dashboard
📋 SHIFT HANDOVER DASHBOARD
📅 Date: |  | 👤 Duty Manager: |  | 📆 Week:
SHIFT STATUS OVERVIEW
| 🌅 SHIFT 1 |  | ☀️ SHIFT 2 |  | 🌙 SHIFT 3
PROJECT | Status | Lead | Status | Lead | Status | Lead
📁 CONTENT
📧 EMAIL
💬 MESSAGING
📊 DAILY METRICS
Metric | Content | Email | Messaging | TOTAL
Total Tickets Today |  |  |  | 0
Open Issues |  |  |  | 0
Resolved |  |  |  | 0
Escalations/ |  |  |  | 0
📝 DUTY MANAGER NOTES
Key Issues / Escalations:
Actions for Tomorrow:

## Content
📁 CONTENT - SHIFT HANDOVER
📅 Date: | 2026-04-03 | Total Clients: |  | 24
SHIFT 1 (Morning) ¦ 5:00 AM - 2:00 PM
Client | Tickets | Status | Engineer Worked | Issues | Updates | Handover | Engineer
Syndis
Washington Post | L2B-11531,L2B-11478,L2B-11629,L2B-11631,L2B-11210,L2B-11213,L2B-11260,L2B-11263,L2B-11734,L2B-11735,L2B-11737and L2B-11738 | ⏳ In Progress |  | drive chnaged tickets and retry folders and confilts | no update no those tickets from dev side | track these tickets,
Nom Nom
travelier(BookAway)
Renovus Capital
Tunnel to Towers
Ole Smoky
ceribell (3) | nill | ✅ Complete |  | Nill | In Server 2 Delta intiated for 16 pairs | please monitor the delta
ELC Beauty (estee)
KnoxCounty | Nill | ✅ Complete |  | Nill | Final Delta Migration Completed | Help client if he need any assistance
Michigan Economic
Chryselis
Tellepsen
B&B Electric
Armstrong
Convex | nill | ✅ Complete |  | Nill
Corc Systems | Nill | ✅ Complete |  | Nill | Final Delta completed and updated to client. We are at post migration support part | Help client if he need any assistance
Duet Resource
Cumulous Global
Peak Mining | L2B-11673 | ⏳ In Progress |  | file are not moving | siva kota update the comment still dev team need to retry the conflicts | Follow up the ticket and monitor the migrations
Pdf Solutions
CEG
Vendasta
Epiq
SHIFT TOTAL | 0 |  |  |  | Lead:
SHIFT 2 (Afternoon) ¦ 1:00 PM - 10:00 PM
Client | Tickets | Status | Engineer Worked | Issues | Updates | Handover | Engineer
Syndis |  |  |  |  | Waiting for decommission approval
Washington Post | L2B-11478,11259,11207,11296,11260,11210,525,11263,11213,11414 | ⏳ In Progress |  | File Rate Limit, Last Versions | Pre Delta initited for 3 servers, and onetime is going on | Follow up the tickets and monitor collabs and links | Harshith
Nom Nom | L2B-11756 | ⏳ In Progress |  | File/Folder conflicts Retry | Retried manual file conflicts, permissions and hyperlinks | Need to follow up on that ticket and work on the WS status update | Vishnu
travelier(BookAway) | L2B-11174 | ⏳ In Progress |  | Mayank is working on this ticket | Followed up on the ticket | Follow up on the ticket | Amulya
Renovus Capital |  |  |  |  | Waiting for the decommission approval | Raise decommission request if we got approval | Harshith
Tunnel to Towers | L2B-11528,11281,11420 and L2B-11747 | ⏳ In Progress |  | Folder conflict, Rate limit, Last version retry | Onetime migration is in process. Working on cleanup part. | Follow up the tickets & clear permission & links | Vishnu
Ole Smoky |  |  |  |  | We got an update sheet from the client and started validating the paths | Validate the sheet and start the migration | Vishnu
ceribell (3) |  |  |  |  | Monitored the delta migration and it got completed | Monitor the remaining one-time pairs | Amulya
ELC Beauty (estee) | L2B-11748 | ⏳ In Progress |  | Folders struck in InProgress and not processed | Onetime migration is in process. Initiating pairs on batch wise | Follow up the ticket and monitor the migrations | Harshith
KnoxCounty | NIL | ✅ Complete |  | NIL | Final Delta completed and updated to client. We are at post migration support part | Help client if he need any assistance | Amulya
Michigan Economic | L2B-11443 | ⏳ In Progress |  | Folder conflict, WS in conflict, Getting rate limit | Monitored the one-time migration and followed on the ticket | Follow up the ticket, work on issues and monitor the migrations | Amulya
Chryselis | L2B-11335,11519,481,11342,6304,11255,11125 | ⏳ In Progress |  | Missing files & folders, Long file name links, Drive changes | Onetime migration is in process. Initiating pairs on batch wise | Follow up the ticket, work on issues and monitor the migrations | Harshith
Tellepsen | L2B-6234 | ✅ Complete |  | Folder conflicts and manual folder retry | Followed up on the ticket and updated to the manager | Issue is related to Quota limit and needs to update to client | Siva Kota
B&B Electric |  |  |  |  | Pending with final validation from client |  | Siva Kota
Armstrong | NIL | ✅ Complete |  | NIL | Final Delta completed and updated to client. We are at post migration support part | Help client if he need any assistance | Amulya
Convex | NIL | ✅ Complete |  | Drive level Permission Issues - POC | POC is in progress | Help Dev & Anthony if any assistance needed | Amulya
Corc Systems | NIL | ✅ Complete |  | NIL | Final Delta completed and updated to client. We are at post migration support part | Help client if he need any assistance | Vishnu
Vatica Content | [6 empty] | Siva Kota
Duet Resource |  |  |  |  | Test pair migration was completed, and we are waiting for another batch |  | Siva Kota
Cumulous Global | L2B-11700, L2B-11703 and L2B-11706 | ⏳ In Progress |  | Folder and file conflict retry | Monitored the project and followed up on tickets | Follow up on the tickets and monitor the migration | Harshith
Peak Mining | L2B-11673 | ⏳ In Progress |  | Versions retry | Followed up on the ticket and monitored the migration | Follow up on the ticket and monitor the migration | Amulya
Pdf Solutions | L2B-11750 | ⏳ In Progress |  | Folder conflict and getting Activity Limit Reached | Onetime migration is in process. Initiating pairs on batch wise | Follow up the ticket, work on issues and monitor the migrations | Harshith
Vendasta |  |  |  |  | One-Time completed |  | Amulya
Future Range |  | ⏳ In Progress |  | retrying for conflict files | final delta today and one time is going on for 2pairs | monitor delta pairs | Harshith
Epiq | [6 empty] | Siva Kota
SHIFT TOTAL | 0 |  |  |  | Lead : SRIRAM
SHIFT 3 (Night) ¦ 9:00 PM - 6:00 AM
Client | Tickets | Status | Engineer Worked | Issues | Updates | Handover | Engineer
Syndis
Washington Post | ⏳ In Progress |  | File Rate Limit, Last Versions | Pre Delta initited for 3 servers, and onetime is going on | Follow up the tickets and monitor collabs and links | follow up all the server tickets and initiate delta for sever 1 mentioned pairs in group
Nom Nom | L2B-11756, L2B-11769 | ⏳ In Progress |  | File/Folder conflicts Retry | Retried manual file conflicts, permissions and hyperlinks | Need to follow up on that ticket and work on the WS status update
travelier(BookAway) | L2B-11174 |  |  |  |  | NA
Renovus Capital
Tunnel to Towers | NIL | ✅ Complete |  | NIL | Onetime migration is in process. Initiating pairs on batch wise | Need to update WS
Ole Smoky | [5 empty] | We got an update sheet from the client and started validating the paths |  | Validate the sheet and start the migration
ceribell (3) | NIL | ⏳ In Progress |  | NIL | Onetime migration has been completed for 2 jobs need to initiate the delta | Monitor the 6 jobs from 2 servers
ELC Beauty (estee) | L2B-11748 | ⏳ In Progress |  | Folders struck in InProgress and not processed | Onetime migration is in process. Initiating pairs on batch wise | Follow up the ticket and monitor the migrations
KnoxCounty
Michigan Economic | L2B - 11443 | ✅ Complete |  | for sd to spo destination getting ratelimit while uploading the csv file | Client provided the users completed the one time and need to initiate the delta | Upload the SD to SPO csv file and initiate the delta
Chryselis | L2B-11335,11519,481,11342,6304,11255,11125 | ⏳ In Progress |  | Missing files & folders, Long file name links, Drive changes | Onetime migration is in process. Initiating pairs on batch wise | Follow up the ticket, work on issues and monitor the migrations
Tellepsen | NL |  |  |  | Initiated migration | monitor the migration
B&B Electric |  |  |  |  | Decommissioned the server
Armstrong
Convex
Corc Systems | NIL | ✅ Complete |  | NIL | Final Delta completed and updated to client. We are at post migration support part | Help client if he need any assistance
Duet Resource
Cumulous Global | NIL | ✅ Complete |  | NIL | Onetime migration is in process. Initiating pairs on batch wise | work on issues and monitor the migrations
Peak Mining | L2B-11673 | ⏳ In Progress |  | files are not mnoving | added comment in the ticket | follow up the ticket and monitor the migrations
Pdf Solutions | L2B-11750 | ⏳ In Progress |  | Folder conflict and getting Activity Limit Reached | Onetime migration is in process. Initiating pairs on batch wise | NA
CEG
Vendasta | [5 empty] | few users left need to confirm with client for initiation
Epiq |  |  |  |  | client gave permission mapping | manager will drop a mail regarding the csv and some issues
SHIFT TOTAL | 0 |  |  |  | Lead:

## 04-04-26
📁 CONTENT - SHIFT HANDOVER
📅 Date: | 2026-04-03 | Total Clients: |  | 24
SHIFT 1 (Morning) ¦ 5:00 AM - 2:00 PM
Client | Tickets | Status | Engineer Worked | Issues | Updates | Handover | Engineer
Syndis
Washington Post | [L2B-11786] | ⏳ In Progress |  | Change the ws Status | Please check the ticket and update the info which developer asked
Nom Nom | L2B-11769 | ⏳ In Progress | ⏳ In Progress | Retry conflict files | Please Followup the ticket and monitor the email migration
travelier(BookAway) | Nill |  |  | Nill
Renovus Capital
Tunnel to Towers
Ole Smoky
ceribell (3)
ELC Beauty (estee) | [L2B-11787], [L2B-11777] | ⏳ In Progress | ⏳ In Progress | Files are moving slow and retry conflict | Please followup these tickets and monitor the migration and validate the onedrive pairs, I tried but didn't got result
KnoxCounty | Nill |  |  | Final Delta Completed
Michigan Economic
Chryselis | Nill | Delta | Chaitanya | Delta migration is gng on, Need to check the collabs and permissions | Please don't the enable anything, there is some different process we follow
Tellepsen
B&B Electric
Armstrong
Convex
Corc Systems
Duet Resource
Cumulous Global
Peak Mining
Pdf Solutions | L2B-11781 , L2B-11783 , L2B-11785 | ⏳ In Progress |  | filefolders , folders And permitions are in conflicts | created a ticket for all conflicts | follow up the ticket and check the migartion
CEG
Vendasta
Epiq
SHIFT TOTAL | 0 |  |  |  | Lead:
SHIFT 2 (Afternoon) ¦ 1:00 PM - 10:00 PM
Client | Tickets | Status | Engineer Worked | Issues | Updates | Handover | Engineer
Syndis
Washington Post
Nom Nom
travelier(BookAway)
Renovus Capital
Tunnel to Towers
Ole Smoky
ceribell (3)
ELC Beauty (estee)
KnoxCounty
Michigan Economic
Chryselis
Tellepsen
B&B Electric
Armstrong
Convex
Corc Systems
Vatica Content
Duet Resource
Cumulous Global
Peak Mining
Pdf Solutions
Vendasta
Future Range
Epiq
SHIFT TOTAL | 0 |  |  |  | Lead : SRIRAM
SHIFT 3 (Night) ¦ 9:00 PM - 6:00 AM
Client | Tickets | Status | Engineer Worked | Issues | Updates | Handover | Engineer
Syndis
Washington Post
Nom Nom
travelier(BookAway)
Renovus Capital
Tunnel to Towers
Ole Smoky
ceribell (3)
ELC Beauty (estee)
KnoxCounty
Michigan Economic
Chryselis
Tellepsen
B&B Electric
Armstrong
Convex
Corc Systems
Duet Resource
Cumulous Global
Peak Mining
Pdf Solutions
CEG
Vendasta
Epiq
SHIFT TOTAL | 0 |  |  |  | Lead:

## 05-04-26
📁 CONTENT - SHIFT HANDOVER
📅 Date: | 2026-04-05 | Total Clients: |  | 24
SHIFT 1 (Morning) ¦ 5:00 AM - 2:00 PM
Client | Tickets | Status | Engineer Worked | Issues | Updates | Handover | Engineer
Syndis |  | ✅ Complete | vineetha |  | waiting for validation
Washington Post | [L2B-11786] | ⏳ In Progress |  | Change the ws Status | Please check the ticket and update the info which developer asked
Nom Nom | L2B-11769 | ⏳ In Progress | ⏳ In Progress | Retry conflict files | Please Followup the ticket and monitor the email migration
travelier(BookAway) | Nill |  |  | Nill
Renovus Capital
Tunnel to Towers
Ole Smoky
ceribell (3) | Nill | ✅ Complete |  |  | delta pairs in server 2 are processed and update to client | please monitor the other servers
ELC Beauty (estee) | [L2B-11787], [L2B-11777] | ⏳ In Progress | ⏳ In Progress | Files are moving slow and retry conflict | Please followup these tickets and monitor the migration and validate the onedrive pairs, I tried but didn't got result
KnoxCounty | delta done | ✅ Complete | vineetha | Final Delta Completed | Waiting for decommission the server
Michigan Economic | Nill | ✅ Complete |  |  | Delta pair intiated for box to od | please monitor the delta And create a ticket is
Chryselis | Nill | Delta | Chaitanya | Delta migration is gng on, Need to check the collabs and permissions | Please don't the enable anything, there is some different process we follow
Tellepsen
B&B Electric
Armstrong
Convex
Corc Systems | Nill | ✅ Complete |  |  | Delta migration completed
Duet Resource
Cumulous Global
Peak Mining
Pdf Solutions
CEG
Vendasta
Duncan group | L2B-11816 | ⏳ In Progress | vineetha | folder conflicts and manual folder retry | One time migration is going on both one-onedrive and spo-spo
Cadence |  | ✅ Complete | vineetha |  | pilot migration has been completed
Epiq | Delta done | ✅ Complete | vineetha
SHIFT TOTAL | 0 |  |  |  | Lead:
SHIFT 2 (Afternoon) ¦ 1:00 PM - 10:00 PM
Client | Tickets | Status | Engineer Worked | Issues | Updates | Handover | Engineer
Syndis
Washington Post
Nom Nom
travelier(BookAway)
Renovus Capital
Tunnel to Towers
Ole Smoky
ceribell (3)
ELC Beauty (estee)
KnoxCounty
Michigan Economic
Chryselis
Tellepsen
B&B Electric
Armstrong
Convex
Corc Systems
Vatica Content
Duet Resource
Cumulous Global
Peak Mining
Pdf Solutions
Vendasta
Future Range
Epiq
SHIFT TOTAL | 0 |  |  |  | Lead : SRIRAM
SHIFT 3 (Night) ¦ 9:00 PM - 6:00 AM
Client | Tickets | Status | Engineer Worked | Issues | Updates | Handover | Engineer
Syndis
Washington Post
Nom Nom
travelier(BookAway)
Renovus Capital
Tunnel to Towers
Ole Smoky
ceribell (3)
ELC Beauty (estee)
KnoxCounty
Michigan Economic
Chryselis
Tellepsen
B&B Electric
Armstrong
Convex
Corc Systems
Duet Resource
Cumulous Global
Peak Mining
Pdf Solutions
CEG
Vendasta
Epiq
SHIFT TOTAL | 0 |  |  |  | Lead: