## Dashboard
📋 SHIFT HANDOVER DASHBOARD
📅 Date: |  | 👤 Duty Manager: |  | 📆 Week:
SHIFT STATUS OVERVIEW
| 🌅 SHIFT 1 |  | ☀️ SHIFT 2 |  | 🌙 SHIFT 3
PROJECT | Status | Lead | Status | Lead | Status | Lead
📁 CONTENT
📧 EMAIL
💬 MESSAGING
📊 DAILY METRICS
Metric | Content | Email | Messaging | TOTAL
Total Tickets Today |  |  |  | 0
Open Issues |  |  |  | 0
Resolved |  |  |  | 0
Escalations/ |  |  |  | 0
📝 DUTY MANAGER NOTES
Key Issues / Escalations:
Actions for Tomorrow:

## Email
📧 EMAIL - SHIFT HANDOVER
📅 Date: | 2026-03-04 | Total Clients: |  | 11
SHIFT 1 (Morning) ¦ 6:00 AM - 2:00 PM
Client | Tickets | Status | Engineer Worked | Issues | Updates | Handover | Engineer
Syndis
Nom Nom
travelier(BookAway)
(tech wizards)
Peak mining
Cumulus Global
PDF | L2B-11744 | ⏳ In Progress |  | Email info conflicts | Email migration is going on. still some pairs are piking going on | work on issues and monitor the migrations
KnoxCounty | nill | ✅ Complete |  | Nill | Migration completed | Help client if he need any assistance
Vatica Email | L2B-11745 | ⏳ In Progress |  | Email folder conflicts | Final Delta is in progress and still emails and folders picking going on | work on issues and monitor the migrations
Rocco Forte
I support the girls | Nill | ✅ Complete |  | Nill | one time All are processed | Client postpone delta for next week
SHIFT TOTAL | 0 |  |  |  | Lead:
SHIFT 2 (Afternoon) ¦ 2:00 PM - 10:00 PM
Client | Tickets | Status | Engineer Worked | Issues | Updates | Handover | Engineer
Nom Nom |  |  |  |  | Monitored the email migration and updated in the group | Monitor and give updates accordingly | siva kota
travelier(BookAway) |  |  |  |  | Delta migration completed and waiting for the client to validate |  | siva kota
(tech wizards) | L2B-11761 | ⏳ In Progress |  | Retry email conflicts | Monitored the email migration and updated in the group | Monitor and give updates accordingly | vishnu
Duncan Group |  | ⏳ In Progress |  | Request to upload the Permission Mapping | Pilot Migration Is Completed, Once Permission Mapping Completes based on customer confirmation need to start the One-time | Follow up the ticket and check with Harika about the One-time Migration | siva kota
Peak mining | [6 empty] | siva kota
Cumulus Global |  |  |  |  | Initiated pilot migration | Monitor the migration | siva kota
PDF | NIL | ✅ Complete |  | NIL | Onetime migration is in process. Initiating pairs on batch wise | work on issues and monitor the migrations | siva kota
KnoxCounty | NIL | ✅ Complete |  | NIL | Final Delta completed and updated to client. We are at post migration support part | Help client if he need any assistance | siva kota
Vatica Email | L2B-11745 | ✅ Complete |  |  | Retreid conflicts and a few folders need to be renamed in the source | Monitor the migration and need to update to client | siva kota
Rocco Forte Email | L2B-11751, L2B-11753 and L2B-11755 | ⏳ In Progress |  |  | Created tickets and monitored the migration | Follow up on the tickets and monitor the migration | siva kota
SHIFT TOTAL | 0 |  |  |  | Lead:
SHIFT 3 (Night) ¦ 10:00 PM - 6:00 AM
Client | Tickets | Status | Engineer Worked | Issues | Updates | Handover | Engineer
Syndis |  |  |  |  | Waiting for validation from client
Nom Nom |  |  |  |  | Monitored the email migration and updated in the group | Monitor and give updates accordingly
travelier(BookAway) |  |  |  |  | Delta migration completed and waiting for the client to validate
(tech wizards) | L2B-11761 | ⏳ In Progress |  | Retry email conflicts | Monitored the email migration and updated in the group | Monitor and give updates accordingly
Peak mining
Cumulus Global |  |  |  |  | Initiated pilot migration | Monitor the migration
PDF | NL | ✅ Complete |  |  | Onetime migration is in process. Initiating pairs on batch wise | work on issues and monitor the migrations
KnoxCounty | [5 empty] | Help client if he need any assistance
Vatica Email | L2B-11745 | ✅ Complete |  |  | Retreid conflicts and a few folders need to be renamed in the source | Monitor the migration and need to update to client
Rocco Forte | L2B-11719 ,L2B-11751, L2B-11753 and L2B-11755 | In progress |  | Claendar event missing | Created tickets and monitored the migration | Follow up the ticket and monitor the migration
I support the girls |  |  |  |  | Customer confirmed to postpone the delta to next week | Follow up on the tickets and monitor the migration
SHIFT TOTAL | 0 |  |  |  | Lead:

## 04-04-26
📧 EMAIL - SHIFT HANDOVER
📅 Date: | 2026-03-04 | Total Clients: |  | 11
SHIFT 1 (Morning) ¦ 6:00 AM - 2:00 PM
Client | Tickets | Status | Engineer Worked | Issues | Updates | Handover | Engineer
Syndis | nill | ✅ Complete |  | nill
Nom Nom
travelier(BookAway) | Nill |  |  |  | Delta migration completed and waiting for the client to validate
(tech wizards) | L2B-11774 | ⏳ In Progress |  | Email info & Email folder conflicts | migratio is going on, i cretae ticket for conflicts | Follow up the ticket and manitor the migration
Peak mining | Nill |  |  | nill | one time migration completed
Cumulus Global
PDF | L2B-11773 | ⏳ In Progress |  | Email info & Email folder conflicts | migration is going on i create da ticket for conflicts | Follow up the ticket and manitor the migration | Ramana
KnoxCounty | Nill | ✅ Complete |  | Nill | Final Delta Completed | Help client if he need any assistance
Vatica Email | Nill | ✅ Complete |  | nill | Still Email piking & Eamil folders is going on in both servers in delta | manitor the migartion & Create a ticket is there any conflicts
Rocco Forte
I support the girls |  |  |  |  | Customer confirmed to postpone the delta to next week
SHIFT TOTAL | 0 |  |  |  | Lead:
SHIFT 2 (Afternoon) ¦ 2:00 PM - 10:00 PM
Client | Tickets | Status | Engineer Worked | Issues | Updates | Handover | Engineer
Nom Nom
travelier(BookAway)
(tech wizards)
Duncan Group
Peak mining
Cumulus Global
PDF
KnoxCounty
Vatica Email
Rocco Forte Email
SHIFT TOTAL | 0 |  |  |  | Lead:
SHIFT 3 (Night) ¦ 10:00 PM - 6:00 AM
Client | Tickets | Status | Engineer Worked | Issues | Updates | Handover | Engineer
Syndis
Nom Nom
travelier(BookAway)
(tech wizards)
Peak mining
Cumulus Global
PDF
KnoxCounty
Vatica Email
Rocco Forte
I support the girls
SHIFT TOTAL | 0 |  |  |  | Lead:

## 05-04-26
📧 EMAIL - SHIFT HANDOVER
📅 Date: | 2026-04-05 | Total Clients: |  | 11
SHIFT 1 (Morning) ¦ 6:00 AM - 2:00 PM
Client | Tickets | Status | Engineer Worked | Issues | Updates | Handover | Engineer
Syndis | nill | ✅ Complete |  | nill
Nom Nom
travelier(BookAway) | Nill | ✅ Complete |  |  | Delta migration completed and waiting for the client to validate
(tech wizards) | L2B-11820 | ⏳ In Progress |  | Email info conflicts | migration is going on i created a ticket for conflicts | Follow up the ticket and manitor the migration
Peak mining | Nill | ✅ Complete |  | nill | one time migration completed
Cumulus Global
PDF | L2B-11813 | ⏳ In Progress |  | Email info conflicts | migration is going on i created a ticket for conflicts | Follow up the ticket and manitor the migration
KnoxCounty | Nill | ✅ Complete |  | Nill | Final Delta Completed | Help client if he need any assistance
Vatica Email | L2B-11818 | ⏳ In Progress |  | Email info conflicts | Still Email piking & Eamil folders is going on in both servers in delta | manitor the migartion & Create a ticket is there any conflicts
Rocco Forte
I support the girls | Nill | ✅ Complete |  | Nill | Customer confirmed to postpone the delta to next week
SHIFT TOTAL | 0 |  |  |  | Lead:
SHIFT 2 (Afternoon) ¦ 2:00 PM - 10:00 PM
Client | Tickets | Status | Engineer Worked | Issues | Updates | Handover | Engineer
Nom Nom
travelier(BookAway)
(tech wizards)
Duncan Group
Peak mining
Cumulus Global
PDF
KnoxCounty
Vatica Email
Rocco Forte Email
SHIFT TOTAL | 0 |  |  |  | Lead:
SHIFT 3 (Night) ¦ 10:00 PM - 6:00 AM
Client | Tickets | Status | Engineer Worked | Issues | Updates | Handover | Engineer
Syndis
Nom Nom
travelier(BookAway)
(tech wizards)
Peak mining
Cumulus Global
PDF
KnoxCounty
Vatica Email
Rocco Forte
I support the girls
SHIFT TOTAL | 0 |  |  |  | Lead: