## Migration Plan Content
Task Name | Description | Assigned To | Planned Start Date | Planned End Date | Actual State Date | Actual End Date | Status | Comments | Additional Notes
Kick off Call | Discuss scope, expectations, timelines, pre-requisites | Cloudfuze | 28-01-2026 | 28-01-2026 | 28-01-2026 | 28-01-2026 | Completed
Pre-requisites | Prepare the source and destination ready for migration | Customer/Cloudfuze | 30-01-2026 | 30-01-2026 | 30-01-2026 | 30-01-2026 | Completed
Server Creation | Create the Cloudfuze servers for the Migration | Cloudfuze | 28-01-2026 | 28-01-2026 | 28-01-2026 | 28-01-2026 | Completed
Server Sanity Creation | Server sent for Sanity | Cloudfuze | 28-01-2026 | 29-01-2026 | 28-01-2026 | 30-01-2026 | Completed
Cloud Adding | Connect the CloudFuze tool to Source and Destination | Customer/Cloudfuze | 30-01-2026 | 30-01-2026 | 30-01-2026 | 30-01-2026 | Completed
User Mapping | Map the source user to destination user | Customer/Cloudfuze | 30-01-2026 | 30-01-2026 | 30-01-2026 | 30-01-2026 | Completed
Permission Mapping | Permissions mapping | Customer/Cloudfuze | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | Completed
Pilot Migration |  | Cloudfuze | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | Completed
One Time Migration |  | Cloudfuze
Server 1( Batch 1,2,3) |  | Cloudfuze
| Batch 1 |  |  |  | 2026-02-10 | 2026-02-10 | Completed
| Batch 2 |  |  |  | 2026-02-12 | 2026-03-10 | Completed
| Batch 3 |  |  |  | 2026-02-13 | 2026-03-10 | Completed
| Batch 4 |  |  |  | 2026-03-03 | 2026-03-10 | Completed
| Batch 5 |  |  |  | 2026-03-04 | 2026-03-04 | Completed
One time Validation |  | Customer
|  | Customer | [5 empty] | Hyperlinks
|  | Customer | [5 empty] | Folders structure
|  | Customer | [5 empty] | Permissions
|  | Customer | [5 empty] | Files
Delta Aproval |  | Customer | [5 empty] | Mention approval date
Delta Validation |  | Customer/Cloudfuze
|  | Customer | [5 empty] | Hyperlinks
|  | Customer | [5 empty] | Folders structure
|  | Customer | [5 empty] | Permissions
|  | Customer | [5 empty] | Files
Project Closure |  | Customer/Cloudfuze

## Issue Tracker
Date | Description | L3 Ticket | Ticket Status | Resolved Date | Resolution | CFITS Ticket | Days to solve
28-01-2026 | Server Creation | https://cf2020.atlassian.net/browse/IB-1642 | Resolved | 28-01-2026 |  | https://cf2020.atlassian.net/browse/IB-1642 | 1
28-01-2026 | Sanity test | https://cf2020.atlassian.net/browse/QAB-607 | Resolved | 2026-01-29 |  | https://cf2020.atlassian.net/browse/QAB-607 | 2
2026-02-09 | Validation issue | https://cf2020.atlassian.net/browse/L2B-510 | Resolved | 2026-02-11 |  | https://cf2020.atlassian.net/browse/CFITS-3026 | 1
2026-02-13 | Validation issue | https://cf2020.atlassian.net/browse/L2B-700 | Resolved | 2026-02-13 |  | https://cf2020.atlassian.net/browse/CFITS-3183 | 1
2026-02-13 | Retry file conflicts | https://cf2020.atlassian.net/browse/PRI-10760 | Resolved | 2026-02-13 |  | https://cf2020.atlassian.net/browse/CFITS-3195 | 1
2026-02-13 | folder conflict | https://cf2020.atlassian.net/browse/PRI-10759 | Resolved | 2026-02-13 |  | https://cf2020.atlassian.net/browse/CFITS-3194 | 1
2026-02-15 | Retry file conflicts | https://cf2020.atlassian.net/browse/PRI-10838 | Resolved | 2026-02-19 |  |  | 4
2026-02-18 | Retry folder conflicts | https://cf2020.atlassian.net/browse/PRI-10930 | Resolved | 2026-03-03 |  | https://cf2020.atlassian.net/browse/CFITS-3336 | 13
2026-02-20 | Release permissions | https://cf2020.atlassian.net/browse/PRI-11031 | Resolved | 2026-02-20 |  | https://cf2020.atlassian.net/browse/CFITS-3431 | 1
2026-02-27 | Release Hyperlinks | https://cf2020.atlassian.net/browse/PRI-11295 | Resolved | 2026-03-01 |  | https://cf2020.atlassian.net/browse/CFITS-3668 | 3
2026-03-02 | Update Drive changes | https://cf2020.atlassian.net/browse/PRI-11400 | Resolved | 2026-03-03 |  | https://cf2020.atlassian.net/browse/CFITS-3750 | 1
2026-03-03 | Update Ws status | https://cf2020.atlassian.net/browse/PRI-11412 | Resolved | 2026-03-05 |  | https://cf2020.atlassian.net/browse/CFITS-3763 | 2
2026-03-03 | Suspend WS | https://cf2020.atlassian.net/browse/PRI-11432 | Resolved | 2026-03-03 |  | https://cf2020.atlassian.net/browse/CFITS-3779 | 1
2026-03-09 | Update Drive changes | https://cf2020.atlassian.net/browse/PRI-11663 | Resolved | 2026-03-10 |  | https://cf2020.atlassian.net/browse/CFITS-3993 | 1

## Migration Tracker
source email | Source Path | Destination Email id | Destination Path | Source Validation | Destination Validation | Migration status | Combination | server | Comments
admin@getbybus.com | / | admin@travelier.com | / | PASS | PASS | Initated migartion | MyDrive - MyDrive
ante@traveling.com | / | ante@travelier.com | / | PASS | PASS | Initated migartion | MyDrive - MyDrive
ante.domjanovic@traveling.com | / | ante.domjanovic@travelier.com | / | PASS | PASS | Initated migartion | MyDrive - MyDrive
antea.kuduz@traveling.com | / | antea.kuduz@travelier.com | / | PASS | PASS | Initated migartion | MyDrive - MyDrive
antonia.petricevic@traveling.com | / | antonia.petricevic@travelier.com | / | PASS | PASS | Initated migartion | MyDrive - MyDrive
danijela.boljat@traveling.com | / | danijela.boljat@travelier.com | / | PASS | PASS | Initated migartion | MyDrive - MyDrive
dpo@traveling.com | / | dpo@travelier.com | / | PASS | PASS | Initated migartion | MyDrive - MyDrive
ella.tafra@traveling.com | / | ella.tafra@travelier.com | / | PASS | PASS | Initated migartion | MyDrive - MyDrive
ema.uvodic@traveling.com | / | ema.uvodic@travelier.com | / | PASS | PASS | Initated migartion | MyDrive - MyDrive
ex-employee@getbybus.com | / | ex-employee@travelier.com | / | PASS | PASS | Initated migartion | MyDrive - MyDrive
gbb-dev-office@getbybus.com | / | gbb-dev-office@travelier.com | / | PASS | PASS | Pilot Completed | MyDrive - MyDrive
gcp-svc-readonly-user@traveling.com | / | gcp-svc-readonly-user@travelier.com | / | PASS | PASS | Initated migartion | MyDrive - MyDrive
info@getbybus.com | / | info-gbb@travelier.com | / | PASS | PASS | Initated migartion | MyDrive - MyDrive
no-reply@getbybus.com | / | no-reply@travelier.com | / | PASS | PASS | Initated migartion | MyDrive - MyDrive
info@getbyferry.com | / | info-gbf@travelier.com | / | PASS | PASS | Initated migartion | MyDrive - MyDrive
info@getbytransfer.com | / | info-gbtransfer@travelier.com | / | PASS | PASS | Initated migartion | MyDrive - MyDrive
hrvoje.zvonaric@traveling.com | / | hrvoje.z@travelier.com | / | PASS | PASS | Initated migartion | MyDrive - MyDrive
ivan@traveling.com | / | ivan@travelier.com | / | PASS | PASS | Initated migartion | MyDrive - MyDrive
ivana.varmuza@traveling.com | / | ivana.varmuza@travelier.com | / | PASS | PASS | Initated migartion | MyDrive - MyDrive
ivana.kozul@traveling.com | / | ivana.kozul@travelier.com | / | PASS | PASS | Initated migartion | MyDrive - MyDrive
jerko.zaneta@traveling.com | / | jerko.z@travelier.com | / | PASS | PASS | Initated migartion | MyDrive - MyDrive
josip.odrljin@traveling.com | / | josip.odrljin@travelier.com | / | PASS | PASS | Initated migartion | MyDrive - MyDrive
kristina.vukorepa@traveling.com | / | kristina.vukorepa@travelier.com | / | PASS | PASS | Initated migartion | MyDrive - MyDrive
luka.lalic@traveling.com | / | luka.lalic@travelier.com | / | PASS | PASS | Initated migartion | MyDrive - MyDrive
luka.marinkovic@traveling.com | / | luka.m@travelier.com | / | PASS | PASS | Initated migartion | MyDrive - MyDrive
luka.dijan@traveling.com | / | luka.d@travelier.com | / | PASS | PASS | Initated migartion | MyDrive - MyDrive
maja@traveling.com | / | maja@travelier.com | / | PASS | PASS | Initated migartion | MyDrive - MyDrive
marketing@traveling.com | / | marketing@travelier.com | / | PASS | PASS | Initated migartion | MyDrive - MyDrive
matej.mucic@traveling.com | / | matej.mucic@travelier.com | / | PASS | PASS | Initated migartion | MyDrive - MyDrive
mia.jadric@traveling.com | / | mia.jadric@travelier.com | / | PASS | PASS | Initated migartion | MyDrive - MyDrive
michael.cvitkovic@traveling.com | / | michael.cvitkovic@travelier.com | / | PASS | PASS | Initated migartion | MyDrive - MyDrive
morten@getbybus.com | / | morten@travelier.com | / | PASS | PASS | Initated migartion | MyDrive - MyDrive
official@traveling.com | / | official@travelier.com | / | PASS | PASS | Initated migartion | MyDrive - MyDrive
tereza@traveling.com | / | tereza@travelier.com | / | PASS | PASS | Initated migartion | MyDrive - MyDrive
toni.dukic@traveling.com | / | toni.dukic@travelier.com | / | PASS | PASS | Initated migartion | MyDrive - MyDrive
info@traveling.com | / | info-trvl@travelier.com | / | PASS | PASS | Initated migartion | MyDrive - MyDrive
vivian@traveling.com | / | vivian.l@travelier.com | / | PASS | PASS | Initated migartion | MyDrive - MyDrive
zorica.grmoja@traveling.com | / | zorica.g@travelier.com | / | PASS | PASS | Initated migartion | MyDrive - MyDrive
ivan@traveling.com | /Brac | ivan@travelier.com | /Brac | PASS | PASS | Initiated one time | SharedDrive - SharedDrive
toni.dukic@traveling.com | /Email marketing | toni.dukic@travelier.com | /Email marketing | PASS | PASS | Initiated one time | SharedDrive - SharedDrive
ivan@traveling.com | /GetBy-Archive-Vault | ivan@travelier.com | /GetBy-Archive-Vault | PASS | PASS | Initiated one time | SharedDrive - SharedDrive
ivan@traveling.com | /GetBy-Backups-Vault | ivan@travelier.com | /GetBy-Backups-Vault | PASS | PASS | Initiated one time | SharedDrive - SharedDrive
ivan@traveling.com | /GetBy-Design | ivan@travelier.com | /GetBy-Design | PASS | PASS | Initiated one time | SharedDrive - SharedDrive
ivan@traveling.com | /GetBy-GDrive | ivan@travelier.com | /GetBy-GDrive | PASS | PASS | Initiated one time | SharedDrive - SharedDrive
ivan@traveling.com | /GetBy-Photos | ivan@travelier.com | /GetBy-Photos | PASS | PASS | Initiated one time | SharedDrive - SharedDrive
ivan@traveling.com | /GetBy-RnD-Vault | ivan@travelier.com | /GetBy-RnD-Vault | PASS | PASS | Initiated one time | SharedDrive - SharedDrive
ivan@traveling.com | /GetBy-System-Issues | ivan@travelier.com | /GetBy-System-Issues | PASS | PASS | Initiated one time | SharedDrive - SharedDrive
ivan@traveling.com | /test | ivan@travelier.com | /test | PASS | PASS | Initiated one time | SharedDrive - SharedDrive
ivan@traveling.com | /test-trvl12go-shared-drive | ivan@travelier.com | /test-trvl12go-shared-drive | PASS | PASS | Initiated one time | SharedDrive - SharedDrive
ante@traveling.com | /Travelier shared drive | ivan@travelier.com | /Travelier shared drive | PASS | PASS | Initiated one time | SharedDrive - SharedDrive
ivan@traveling.com | /TRVL-API-Integrations | ivan@travelier.com | /TRVL-API-Integrations | PASS | PASS | Initiated one time | SharedDrive - SharedDrive
ivan@traveling.com | /TRVL-Department-RnD | ivan@travelier.com | /TRVL-Department-RnD | PASS | PASS | Initiated one time | SharedDrive - SharedDrive
ivan@traveling.com | /TRVL-TravelingDotCom-GDrive | ivan@travelier.com | /TRVL-TravelingDotCom-GDrive | PASS | PASS | Initiated one time | SharedDrive - SharedDrive
ivan@traveling.com | /Hvar 2023 | ivan@travelier.com | /Hvar 2023 | PASS | PASS | Initiated one time | SharedDrive - SharedDrive
ivan@traveling.com | /Split-Hvar Ferry Youtube | ivan@travelier.com | /Split-Hvar Ferry Youtube | PASS | PASS | Initiated one time | SharedDrive - SharedDrive

## Batch Calendar
Customer Name | TestCustomer | %Completed
Date |  | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-14 | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12
Batch Name | PIlot migration
No. of Conflicts |  | 0 | 0 | 6337 | 6828 | 6710 | 6595 | 6482 | 6364 | 5632 | 5632 | 5632 | 5632 | 5234 | 5120 | 5038 | 4975 | 4975 | 4975 | 4975 | 4959 | 4932 | 4932 | 4932 | 4927 | 4927 | 4927 | 4927 | 4927 | 4927
No. of Remediations |  | 2026-02-13: 3; 2026-02-15: 1; 2026-02-18: 1; 2026-02-20: 1; 2026-02-27: 1; 2026-03-02: 1; 2026-03-03: 2; 2026-03-09: 1
No. of Resolved
No. of Non-Retriable |  | 2026-03-03: 4932; 2026-03-04: 4932
Permissions |  | 8 | 8 | 89104 | 90215 | 92341 | 97166 | 99854 | 104582 | 110394 | 116420 | 118964 | 121776 | 128903 | 134587 | 140255 | 145903 | 151667 | 156739 | 159842 | 167210 | 168034 | 171206 | 171237 | 172215 | 172215 | 172215 | 172215 | 172215 | 172215
Hyperlinks |  | 0 | 0 | 28996 | 29541 | 30876 | 32904 | 35122 | 39810 | 39810 | 42136 | 44782 | 47319 | 50144 | 53627 | 56290 | 59841 | 63275 | 68902 | 72456 | 78133 | 84403 | 103619 | 103884 | 103884 | 103884 | 103884 | 103884 | 103884 | 103884
Start Date | 2026-01-27
End Date | 2026-02-07
ServerName | Server1
Comments
Customer Name | TestCustomer | 2026-02-10: %Completed
Date |  | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-15 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-21 | 2026-03-22 | 2026-03-23
Batch Name | Delta migration
No. of Conflicts |  | 2026-03-12: 594; 2026-03-13: 61
No. of Remediations |  | 2026-03-13: conflict retry
No. of Resolved |  | 2026-03-12: 4555; 2026-03-13: 4555
No. of Non-Retriable |  | 2026-03-13: 61
Permissions |  | 2026-03-12: 4616; 2026-03-13: 4616
Hyperlinks |  | 2026-03-12: 2294; 2026-03-13: 2294
Start Date | 2026-03-12
End Date | 2026-03-13
ServerName | Server1
Comments

## New Batch Calendar
ServerName - quest2 | Important Updates
Batch Name - 1
Start Date - 16-2-2026
End Date -
Migration Type - Onetime/Delta
Customer Name | TRAVELIER | Weekly Status
Date |  | 2026-04-16
|  | Shift-1 (1 PM - 10 PM) | Shift-2 (9 PM - 6 AM) | Shift-3 (6 AM - 2 PM)
Total Pairs |  | 110
Initiated Pairs |  | 110
Completed Pairs |  | 108
Inprogress Pairs |  | 2
Yet to Initiate |  | 0
Processed Folders Count |  | 23967
Inprogress Folders Count |  | 0
Processed Files Count |  | 211660
Inprogress Files Count |  | 0
Processed Data Size |  | 1.8TB
Inprogress Data Size |  | 0
Processed Versions Count |  | 60688
Inprogress Versions Count |  | 0
Processed Permissions Count |  | 177123
Inprogress Permissions Count |  | 0
Processed Hyperlinks Count |  | 106516
Inprogress Hyperlinks Count
No. of Conflicts |  | 4945
No. of Remediations
No. of Resolved
No. of Non-Retriable |  | 4945